## Summary
Vessel | Max wind speed (m/s) | Max Hs (m) | Transit speed (kts) | One-way transit (h) | On-site time (h) | Round-trip window (h) | Build site lat | Build site lon | Build site dist from Dublin (nm) | Build site dist from Dublin (km) | M2 buoy lat | M2 buoy lon | M2 buoy dist from Dublin (nm) | M2 buoy dist from Dublin (km) | Hours wind OK (%) | Hours wave OK (%) | Hours both OK (%) | Qualifying windows (2024)
Crew Transfer Vessel | 12 | 0.9 | 25 | 0.81 | 2 | 4 | 53.6017 | -5.8826 | 20.3 | 37.5 | 53.4836 | -5.4302 | 30.8 | 57 | 87.1 | 54.7 | 54.6 | 224
Jack-up Barge | 10 | 2.5 | 6 | 3.38 | 72 | 79 | 53.6017 | -5.8826 | 20.3 | 37.5 | 53.4836 | -5.4302 | 30.8 | 57 | 75.6 | 92.4 | 75.5 | 59

## Crew_Transfer_V
Window Start | Window End | Duration (h) | Month | Month Name
2024-01-02 14:00 | 2024-01-02 17:00 | 4 | 1 | Jan
2024-01-03 05:00 | 2024-01-03 23:00 | 19 | 1 | Jan
2024-01-04 10:00 | 2024-01-05 13:00 | 28 | 1 | Jan
2024-01-05 15:00 | 2024-01-06 18:00 | 28 | 1 | Jan
2024-01-06 20:00 | 2024-01-08 07:00 | 36 | 1 | Jan
2024-01-11 20:00 | 2024-01-12 18:00 | 23 | 1 | Jan
2024-01-12 20:00 | 2024-01-14 13:00 | 42 | 1 | Jan
2024-01-15 16:00 | 2024-01-16 11:00 | 20 | 1 | Jan
2024-01-16 21:00 | 2024-01-18 04:00 | 32 | 1 | Jan
2024-01-18 09:00 | 2024-01-19 13:00 | 29 | 1 | Jan
2024-01-24 15:00 | 2024-01-24 18:00 | 4 | 1 | Jan
2024-01-24 20:00 | 2024-01-25 01:00 | 6 | 1 | Jan
2024-01-29 03:00 | 2024-01-29 09:00 | 7 | 1 | Jan
2024-01-30 09:00 | 2024-01-31 | 16 | 1 | Jan
2024-02-01 01:00 | 2024-02-01 19:00 | 19 | 2 | Feb
2024-02-03 06:00 | 2024-02-03 18:00 | 13 | 2 | Feb
2024-02-03 20:00 | 2024-02-04 09:00 | 14 | 2 | Feb
2024-02-06 19:00 | 2024-02-08 03:00 | 33 | 2 | Feb
2024-02-10 03:00 | 2024-02-10 08:00 | 6 | 2 | Feb
2024-02-10 15:00 | 2024-02-10 18:00 | 4 | 2 | Feb
2024-02-10 20:00 | 2024-02-11 18:00 | 23 | 2 | Feb
2024-02-11 20:00 | 2024-02-12 14:00 | 19 | 2 | Feb
2024-02-13 04:00 | 2024-02-13 18:00 | 15 | 2 | Feb
2024-02-13 20:00 | 2024-02-14 04:00 | 9 | 2 | Feb
2024-02-15 19:00 | 2024-02-16 18:00 | 24 | 2 | Feb
2024-02-16 20:00 | 2024-02-17 10:00 | 15 | 2 | Feb
2024-02-18 02:00 | 2024-02-18 18:00 | 17 | 2 | Feb
2024-02-18 20:00 | 2024-02-19 18:00 | 23 | 2 | Feb
2024-02-19 20:00 | 2024-02-20 02:00 | 7 | 2 | Feb
2024-02-22 11:00 | 2024-02-22 15:00 | 5 | 2 | Feb
2024-02-22 18:00 | 2024-02-23 01:00 | 8 | 2 | Feb
2024-02-23 14:00 | 2024-02-23 18:00 | 5 | 2 | Feb
2024-02-26 20:00 | 2024-02-27 06:00 | 11 | 2 | Feb
2024-02-27 16:00 | 2024-02-28 06:00 | 15 | 2 | Feb
2024-02-29 09:00 | 2024-02-29 18:00 | 10 | 2 | Feb
2024-03-02 15:00 | 2024-03-04 06:00 | 40 | 3 | Mar
2024-03-05 17:00 | 2024-03-06 08:00 | 16 | 3 | Mar
2024-03-11 10:00 | 2024-03-11 18:00 | 9 | 3 | Mar
2024-03-11 20:00 | 2024-03-11 23:00 | 4 | 3 | Mar
2024-03-15 20:00 | 2024-03-16 09:00 | 14 | 3 | Mar
2024-03-18 06:00 | 2024-03-18 11:00 | 6 | 3 | Mar
2024-03-19 11:00 | 2024-03-19 18:00 | 8 | 3 | Mar
2024-03-19 20:00 | 2024-03-20 18:00 | 23 | 3 | Mar
2024-03-20 20:00 | 2024-03-21 10:00 | 15 | 3 | Mar
2024-03-22 08:00 | 2024-03-22 14:00 | 7 | 3 | Mar
2024-03-24 09:00 | 2024-03-24 20:00 | 12 | 3 | Mar
2024-03-26 03:00 | 2024-03-26 09:00 | 7 | 3 | Mar
2024-03-28 16:00 | 2024-03-28 19:00 | 4 | 3 | Mar
2024-03-29 | 2024-03-29 06:00 | 7 | 3 | Mar
2024-03-31 | 2024-03-31 03:00 | 4 | 3 | Mar
2024-04-01 19:00 | 2024-04-02 17:00 | 23 | 4 | Apr
2024-04-02 19:00 | 2024-04-03 01:00 | 7 | 4 | Apr
2024-04-03 19:00 | 2024-04-04 17:00 | 23 | 4 | Apr
2024-04-08 07:00 | 2024-04-08 17:00 | 11 | 4 | Apr
2024-04-09 20:00 | 2024-04-10 04:00 | 9 | 4 | Apr
2024-04-11 09:00 | 2024-04-11 12:00 | 4 | 4 | Apr
2024-04-13 22:00 | 2024-04-14 17:00 | 20 | 4 | Apr
2024-04-16 12:00 | 2024-04-16 19:00 | 8 | 4 | Apr
2024-04-17 11:00 | 2024-04-18 17:00 | 31 | 4 | Apr
2024-04-18 19:00 | 2024-04-19 17:00 | 23 | 4 | Apr
2024-04-19 19:00 | 2024-04-20 17:00 | 23 | 4 | Apr
2024-04-20 19:00 | 2024-04-21 17:00 | 23 | 4 | Apr
2024-04-21 19:00 | 2024-04-22 17:00 | 23 | 4 | Apr
2024-04-22 19:00 | 2024-04-24 17:00 | 47 | 4 | Apr
2024-04-24 19:00 | 2024-04-27 17:00 | 71 | 4 | Apr
2024-04-27 19:00 | 2024-04-29 03:00 | 33 | 4 | Apr
2024-05-01 08:00 | 2024-05-02 11:00 | 28 | 5 | May
2024-05-02 19:00 | 2024-05-03 17:00 | 23 | 5 | May
2024-05-03 19:00 | 2024-05-05 17:00 | 47 | 5 | May
2024-05-05 19:00 | 2024-05-06 17:00 | 23 | 5 | May
2024-05-06 19:00 | 2024-05-07 17:00 | 23 | 5 | May
2024-05-07 19:00 | 2024-05-08 17:00 | 23 | 5 | May
2024-05-08 19:00 | 2024-05-09 17:00 | 23 | 5 | May
2024-05-09 19:00 | 2024-05-11 17:00 | 47 | 5 | May
2024-05-11 19:00 | 2024-05-12 17:00 | 23 | 5 | May
2024-05-12 19:00 | 2024-05-13 01:00 | 7 | 5 | May
2024-05-14 07:00 | 2024-05-16 08:00 | 50 | 5 | May
2024-05-16 10:00 | 2024-05-16 17:00 | 8 | 5 | May
2024-05-16 19:00 | 2024-05-16 22:00 | 4 | 5 | May
2024-05-17 02:00 | 2024-05-17 17:00 | 16 | 5 | May
2024-05-17 19:00 | 2024-05-21 17:00 | 95 | 5 | May
2024-05-21 19:00 | 2024-05-22 12:00 | 18 | 5 | May
2024-05-24 03:00 | 2024-05-24 17:00 | 15 | 5 | May
2024-05-24 19:00 | 2024-05-26 17:00 | 47 | 5 | May
2024-05-26 19:00 | 2024-05-27 17:00 | 23 | 5 | May
2024-05-27 19:00 | 2024-05-28 01:00 | 7 | 5 | May
2024-05-28 09:00 | 2024-05-28 16:00 | 8 | 5 | May
2024-05-29 04:00 | 2024-05-29 17:00 | 14 | 5 | May
2024-05-29 19:00 | 2024-05-30 01:00 | 7 | 5 | May
2024-05-31 10:00 | 2024-06-01 17:00 | 32 | 5 | May
2024-06-01 19:00 | 2024-06-02 17:00 | 23 | 6 | Jun
2024-06-02 19:00 | 2024-06-03 17:00 | 23 | 6 | Jun
2024-06-03 19:00 | 2024-06-04 14:00 | 20 | 6 | Jun
2024-06-05 | 2024-06-06 17:00 | 42 | 6 | Jun
2024-06-06 19:00 | 2024-06-07 17:00 | 23 | 6 | Jun
2024-06-07 19:00 | 2024-06-08 17:00 | 23 | 6 | Jun
2024-06-08 19:00 | 2024-06-09 17:00 | 23 | 6 | Jun
2024-06-09 19:00 | 2024-06-10 | 6 | 6 | Jun
2024-06-10 13:00 | 2024-06-10 17:00 | 5 | 6 | Jun
2024-06-11 06:00 | 2024-06-11 17:00 | 12 | 6 | Jun
2024-06-11 19:00 | 2024-06-12 17:00 | 23 | 6 | Jun
2024-06-12 19:00 | 2024-06-13 03:00 | 9 | 6 | Jun
2024-06-14 04:00 | 2024-06-14 17:00 | 14 | 6 | Jun
2024-06-14 19:00 | 2024-06-16 17:00 | 47 | 6 | Jun
2024-06-16 19:00 | 2024-06-18 17:00 | 47 | 6 | Jun
2024-06-18 19:00 | 2024-06-19 17:00 | 23 | 6 | Jun
2024-06-19 19:00 | 2024-06-20 17:00 | 23 | 6 | Jun
2024-06-20 19:00 | 2024-06-21 09:00 | 15 | 6 | Jun
2024-06-22 01:00 | 2024-06-23 17:00 | 41 | 6 | Jun
2024-06-23 19:00 | 2024-06-24 12:00 | 18 | 6 | Jun
2024-06-24 23:00 | 2024-06-26 17:00 | 43 | 6 | Jun
2024-06-28 10:00 | 2024-06-29 17:00 | 32 | 6 | Jun
2024-06-29 19:00 | 2024-06-30 17:00 | 23 | 6 | Jun
2024-06-30 19:00 | 2024-07-02 17:00 | 47 | 6 | Jun
2024-07-02 19:00 | 2024-07-03 17:00 | 23 | 7 | Jul
2024-07-04 02:00 | 2024-07-04 07:00 | 6 | 7 | Jul
2024-07-04 22:00 | 2024-07-07 17:00 | 68 | 7 | Jul
2024-07-07 19:00 | 2024-07-09 04:00 | 34 | 7 | Jul
2024-07-10 01:00 | 2024-07-10 17:00 | 17 | 7 | Jul
2024-07-10 19:00 | 2024-07-11 04:00 | 10 | 7 | Jul
2024-07-11 12:00 | 2024-07-11 17:00 | 6 | 7 | Jul
2024-07-11 19:00 | 2024-07-14 17:00 | 71 | 7 | Jul
2024-07-14 19:00 | 2024-07-15 17:00 | 23 | 7 | Jul
2024-07-15 19:00 | 2024-07-17 15:00 | 45 | 7 | Jul
2024-07-20 05:00 | 2024-07-21 17:00 | 37 | 7 | Jul
2024-07-22 04:00 | 2024-07-24 10:00 | 55 | 7 | Jul
2024-07-25 04:00 | 2024-07-25 17:00 | 14 | 7 | Jul
2024-07-25 19:00 | 2024-07-26 17:00 | 23 | 7 | Jul
2024-07-26 19:00 | 2024-07-27 17:00 | 23 | 7 | Jul
2024-07-27 19:00 | 2024-07-28 17:00 | 23 | 7 | Jul
2024-07-28 19:00 | 2024-07-29 17:00 | 23 | 7 | Jul
2024-07-29 19:00 | 2024-08-01 17:00 | 71 | 7 | Jul
2024-08-01 19:00 | 2024-08-02 08:00 | 14 | 8 | Aug
2024-08-03 01:00 | 2024-08-03 17:00 | 17 | 8 | Aug
2024-08-03 19:00 | 2024-08-04 12:00 | 18 | 8 | Aug
2024-08-06 02:00 | 2024-08-06 14:00 | 13 | 8 | Aug
2024-08-07 04:00 | 2024-08-08 14:00 | 35 | 8 | Aug
2024-08-09 06:00 | 2024-08-09 17:00 | 12 | 8 | Aug
2024-08-09 19:00 | 2024-08-12 | 54 | 8 | Aug
2024-08-12 15:00 | 2024-08-12 18:00 | 4 | 8 | Aug
2024-08-13 19:00 | 2024-08-14 17:00 | 23 | 8 | Aug
2024-08-15 19:00 | 2024-08-16 17:00 | 23 | 8 | Aug
2024-08-16 19:00 | 2024-08-17 17:00 | 23 | 8 | Aug
2024-08-17 19:00 | 2024-08-18 17:00 | 23 | 8 | Aug
2024-08-18 19:00 | 2024-08-19 09:00 | 15 | 8 | Aug
2024-08-21 01:00 | 2024-08-21 09:00 | 9 | 8 | Aug
2024-08-22 19:00 | 2024-08-22 22:00 | 4 | 8 | Aug
2024-08-23 13:00 | 2024-08-23 17:00 | 5 | 8 | Aug
2024-08-24 10:00 | 2024-08-25 06:00 | 21 | 8 | Aug
2024-08-26 04:00 | 2024-08-26 13:00 | 10 | 8 | Aug
2024-08-28 19:00 | 2024-08-29 17:00 | 23 | 8 | Aug
2024-08-29 19:00 | 2024-08-31 17:00 | 47 | 8 | Aug
2024-08-31 19:00 | 2024-09-01 | 6 | 8 | Aug
2024-09-01 11:00 | 2024-09-01 17:00 | 7 | 9 | Sep
2024-09-01 19:00 | 2024-09-02 17:00 | 23 | 9 | Sep
2024-09-02 19:00 | 2024-09-04 20:00 | 50 | 9 | Sep
2024-09-04 22:00 | 2024-09-05 03:00 | 6 | 9 | Sep
2024-09-07 01:00 | 2024-09-07 17:00 | 17 | 9 | Sep
2024-09-07 19:00 | 2024-09-08 15:00 | 21 | 9 | Sep
2024-09-09 12:00 | 2024-09-10 03:00 | 16 | 9 | Sep
2024-09-12 13:00 | 2024-09-12 17:00 | 5 | 9 | Sep
2024-09-12 19:00 | 2024-09-13 17:00 | 23 | 9 | Sep
2024-09-15 13:00 | 2024-09-15 17:00 | 5 | 9 | Sep
2024-09-15 19:00 | 2024-09-16 17:00 | 23 | 9 | Sep
2024-09-16 19:00 | 2024-09-17 15:00 | 21 | 9 | Sep
2024-09-17 19:00 | 2024-09-18 17:00 | 23 | 9 | Sep
2024-09-18 19:00 | 2024-09-19 17:00 | 23 | 9 | Sep
2024-09-19 19:00 | 2024-09-21 04:00 | 34 | 9 | Sep
2024-09-22 23:00 | 2024-09-23 17:00 | 19 | 9 | Sep
2024-09-23 19:00 | 2024-09-24 17:00 | 23 | 9 | Sep
2024-09-24 19:00 | 2024-09-25 17:00 | 23 | 9 | Sep
2024-09-28 02:00 | 2024-09-29 03:00 | 26 | 9 | Sep
2024-10-07 20:00 | 2024-10-08 03:00 | 8 | 10 | Oct
2024-10-10 14:00 | 2024-10-10 17:00 | 4 | 10 | Oct
2024-10-10 19:00 | 2024-10-11 17:00 | 23 | 10 | Oct
2024-10-11 19:00 | 2024-10-12 12:00 | 18 | 10 | Oct
2024-10-13 03:00 | 2024-10-13 17:00 | 15 | 10 | Oct
2024-10-14 01:00 | 2024-10-14 05:00 | 5 | 10 | Oct
2024-10-14 11:00 | 2024-10-14 17:00 | 7 | 10 | Oct
2024-10-14 19:00 | 2024-10-15 01:00 | 7 | 10 | Oct
2024-10-16 19:00 | 2024-10-17 05:00 | 11 | 10 | Oct
2024-10-17 19:00 | 2024-10-18 03:00 | 9 | 10 | Oct
2024-10-19 04:00 | 2024-10-19 17:00 | 14 | 10 | Oct
2024-10-22 07:00 | 2024-10-22 17:00 | 11 | 10 | Oct
2024-10-22 19:00 | 2024-10-23 12:00 | 18 | 10 | Oct
2024-10-27 | 2024-10-27 12:00 | 13 | 10 | Oct
2024-10-28 10:00 | 2024-10-28 18:00 | 9 | 10 | Oct
2024-10-28 20:00 | 2024-10-29 18:00 | 23 | 10 | Oct
2024-10-29 20:00 | 2024-11-01 18:00 | 71 | 10 | Oct
2024-11-01 20:00 | 2024-11-02 18:00 | 23 | 11 | Nov
2024-11-02 20:00 | 2024-11-05 17:00 | 70 | 11 | Nov
2024-11-09 | 2024-11-09 18:00 | 19 | 11 | Nov
2024-11-09 20:00 | 2024-11-10 18:00 | 23 | 11 | Nov
2024-11-10 20:00 | 2024-11-12 18:00 | 47 | 11 | Nov
2024-11-12 20:00 | 2024-11-14 18:00 | 47 | 11 | Nov
2024-11-14 20:00 | 2024-11-15 18:00 | 23 | 11 | Nov
2024-11-15 20:00 | 2024-11-17 18:00 | 47 | 11 | Nov
2024-11-17 20:00 | 2024-11-18 17:00 | 22 | 11 | Nov
2024-11-20 15:00 | 2024-11-21 13:00 | 23 | 11 | Nov
2024-11-22 14:00 | 2024-11-22 18:00 | 5 | 11 | Nov
2024-11-22 20:00 | 2024-11-22 23:00 | 4 | 11 | Nov
2024-11-26 02:00 | 2024-11-26 18:00 | 17 | 11 | Nov
2024-11-26 20:00 | 2024-11-27 18:00 | 23 | 11 | Nov
2024-11-27 20:00 | 2024-11-28 07:00 | 12 | 11 | Nov
2024-12-02 21:00 | 2024-12-03 18:00 | 22 | 12 | Dec
2024-12-03 20:00 | 2024-12-04 10:00 | 15 | 12 | Dec
2024-12-06 06:00 | 2024-12-06 12:00 | 7 | 12 | Dec
2024-12-10 08:00 | 2024-12-10 18:00 | 11 | 12 | Dec
2024-12-10 20:00 | 2024-12-11 18:00 | 23 | 12 | Dec
2024-12-11 20:00 | 2024-12-12 18:00 | 23 | 12 | Dec
2024-12-12 20:00 | 2024-12-13 18:00 | 23 | 12 | Dec
2024-12-13 20:00 | 2024-12-14 18:00 | 23 | 12 | Dec
2024-12-15 | 2024-12-15 16:00 | 17 | 12 | Dec
2024-12-16 21:00 | 2024-12-17 02:00 | 6 | 12 | Dec
2024-12-19 21:00 | 2024-12-20 07:00 | 11 | 12 | Dec
2024-12-20 22:00 | 2024-12-21 01:00 | 4 | 12 | Dec
2024-12-23 06:00 | 2024-12-23 18:00 | 13 | 12 | Dec
2024-12-23 20:00 | 2024-12-24 18:00 | 23 | 12 | Dec
2024-12-24 20:00 | 2024-12-25 18:00 | 23 | 12 | Dec
2024-12-25 20:00 | 2024-12-26 18:00 | 23 | 12 | Dec
2024-12-26 20:00 | 2024-12-27 18:00 | 23 | 12 | Dec
2024-12-27 20:00 | 2024-12-28 18:00 | 23 | 12 | Dec
2024-12-28 20:00 | 2024-12-29 18:00 | 23 | 12 | Dec
2024-12-29 20:00 | 2024-12-30 | 5 | 12 | Dec

## Jack-up_Barge
Window Start | Window End | Duration (h) | Month | Month Name
2024-01-02 15:00 | 2024-01-03 23:00 | 33 | 1 | Jan
2024-01-04 07:00 | 2024-01-05 09:00 | 27 | 1 | Jan
2024-01-05 18:00 | 2024-01-06 18:00 | 25 | 1 | Jan
2024-01-06 20:00 | 2024-01-08 12:00 | 41 | 1 | Jan
2024-01-12 20:00 | 2024-01-14 13:00 | 42 | 1 | Jan
2024-01-17 | 2024-01-19 01:00 | 50 | 1 | Jan
2024-02-02 13:00 | 2024-02-03 18:00 | 30 | 2 | Feb
2024-02-06 09:00 | 2024-02-08 01:00 | 41 | 2 | Feb
2024-02-15 12:00 | 2024-02-16 18:00 | 31 | 2 | Feb
2024-02-17 16:00 | 2024-02-18 18:00 | 27 | 2 | Feb
2024-03-03 01:00 | 2024-03-04 15:00 | 39 | 3 | Mar
2024-03-05 10:00 | 2024-03-06 18:00 | 33 | 3 | Mar
2024-03-10 19:00 | 2024-03-11 18:00 | 24 | 3 | Mar
2024-03-25 17:00 | 2024-03-27 06:00 | 38 | 3 | Mar
2024-03-27 21:00 | 2024-03-29 18:00 | 46 | 3 | Mar
2024-03-30 20:00 | 2024-03-31 22:00 | 27 | 3 | Mar
2024-04-17 05:00 | 2024-04-18 17:00 | 37 | 4 | Apr
2024-04-22 19:00 | 2024-04-24 17:00 | 47 | 4 | Apr
2024-04-24 19:00 | 2024-04-26 03:00 | 33 | 4 | Apr
2024-04-26 05:00 | 2024-04-27 17:00 | 37 | 4 | Apr
2024-04-27 19:00 | 2024-04-29 07:00 | 37 | 4 | Apr
2024-04-30 19:00 | 2024-05-02 17:00 | 47 | 4 | Apr
2024-05-03 19:00 | 2024-05-05 17:00 | 47 | 5 | May
2024-05-09 19:00 | 2024-05-11 17:00 | 47 | 5 | May
2024-05-13 19:00 | 2024-05-16 08:00 | 62 | 5 | May
2024-05-17 19:00 | 2024-05-21 17:00 | 95 | 5 | May
2024-05-24 19:00 | 2024-05-26 17:00 | 47 | 5 | May
2024-05-31 | 2024-06-01 17:00 | 42 | 5 | May
2024-06-05 08:00 | 2024-06-06 17:00 | 34 | 6 | Jun
2024-06-14 19:00 | 2024-06-16 17:00 | 47 | 6 | Jun
2024-06-16 19:00 | 2024-06-18 17:00 | 47 | 6 | Jun
2024-06-21 19:00 | 2024-06-23 17:00 | 47 | 6 | Jun
2024-06-24 19:00 | 2024-06-26 17:00 | 47 | 6 | Jun
2024-06-28 06:00 | 2024-06-29 17:00 | 36 | 6 | Jun
2024-06-30 19:00 | 2024-07-02 17:00 | 47 | 6 | Jun
2024-07-06 07:00 | 2024-07-07 17:00 | 35 | 7 | Jul
2024-07-07 19:00 | 2024-07-09 05:00 | 35 | 7 | Jul
2024-07-09 07:00 | 2024-07-10 17:00 | 35 | 7 | Jul
2024-07-11 19:00 | 2024-07-14 17:00 | 71 | 7 | Jul
2024-07-15 19:00 | 2024-07-17 17:00 | 47 | 7 | Jul
2024-07-18 19:00 | 2024-07-19 18:00 | 24 | 7 | Jul
2024-07-19 20:00 | 2024-07-21 17:00 | 46 | 7 | Jul
2024-07-21 19:00 | 2024-07-24 14:00 | 68 | 7 | Jul
2024-07-24 16:00 | 2024-07-25 17:00 | 26 | 7 | Jul
2024-07-29 19:00 | 2024-08-01 17:00 | 71 | 7 | Jul
2024-08-06 19:00 | 2024-08-08 17:00 | 47 | 8 | Aug
2024-08-09 19:00 | 2024-08-13 05:00 | 83 | 8 | Aug
2024-08-23 21:00 | 2024-08-25 05:00 | 33 | 8 | Aug
2024-08-25 19:00 | 2024-08-26 21:00 | 27 | 8 | Aug
2024-08-29 19:00 | 2024-08-31 17:00 | 47 | 8 | Aug
2024-09-02 19:00 | 2024-09-05 16:00 | 70 | 9 | Sep
2024-09-06 03:00 | 2024-09-07 17:00 | 39 | 9 | Sep
2024-09-19 19:00 | 2024-09-21 05:00 | 35 | 9 | Sep
2024-09-27 23:00 | 2024-09-29 04:00 | 30 | 9 | Sep
2024-10-29 20:00 | 2024-11-01 18:00 | 71 | 10 | Oct
2024-11-02 20:00 | 2024-11-06 18:00 | 95 | 11 | Nov
2024-11-10 20:00 | 2024-11-12 18:00 | 47 | 11 | Nov
2024-11-12 20:00 | 2024-11-14 18:00 | 47 | 11 | Nov
2024-11-20 10:00 | 2024-11-21 14:00 | 29 | 11 | Nov

## Monthly_Summary
Vessel | Month | Qualifying Windows
Crew Transfer Vessel | Jan | 14
Crew Transfer Vessel | Feb | 21
Crew Transfer Vessel | Mar | 15
Crew Transfer Vessel | Apr | 16
Crew Transfer Vessel | May | 24
Crew Transfer Vessel | Jun | 24
Crew Transfer Vessel | Jul | 18
Crew Transfer Vessel | Aug | 21
Crew Transfer Vessel | Sep | 19
Crew Transfer Vessel | Oct | 17
Crew Transfer Vessel | Nov | 15
Crew Transfer Vessel | Dec | 20
Jack-up Barge | Jan | 6
Jack-up Barge | Feb | 4
Jack-up Barge | Mar | 6
Jack-up Barge | Apr | 6
Jack-up Barge | May | 6
Jack-up Barge | Jun | 7
Jack-up Barge | Jul | 10
Jack-up Barge | Aug | 5
Jack-up Barge | Sep | 4
Jack-up Barge | Oct | 1
Jack-up Barge | Nov | 4
Jack-up Barge | Dec | 0